## Instructions
Saadiyat Lagoons HSE Scoring Template - Full System Updated
This workbook is structured as a live HSE weekly KPI, dashboard, gap analysis, and CAPA control file. Complete only blue-font input cells or unlocked input fields.
Complete the visible input columns only. Hidden columns calculate automatically.
Score each KPI from 0 to 5. 0 = collapse of control, 5 = excellent sustained control.
Package and Cluster are mandatory. Contractor and responsible team auto-populate.
Weekly_Dashboard is for top management review. Monthly_Dashboard tracks recognition trend.
Gap_Analysis and CAPA_Tracker are for close-out management.
Weekly operating method
1. Enter one line per completed site walk in Weekly_Inspections.
2. Select Package, Cluster, role, high risk activity, and KPI-for-attention fields from dropdown lists only.
3. Score every KPI from 0 to 5. Critical red flag logic reads the gate KPI list directly from KPI_Weights.
4. Use Weekly_Dashboard for current week review, Monthly_Dashboard for recognition/improvement review, Gap_Analysis for weak KPI focus, and CAPA_Tracker for closeout status.
5. Update Close_Date in CAPA_Tracker once the action is fully verified closed. Overdue status updates automatically.
Professional update notes
1. Weekly_Inspections and CAPA_Tracker prepared for full live system use.
2. Filters and freeze panes are enabled on key operational sheets.
3. Dropdown lists added for controlled data entry.
4. Dashboards, gap analysis, and CAPA tracker formulas linked to Weekly_Inspections.
5. Cluster master, lookup lists, and KPI weights can be revised centrally when formally approved.

## Cluster_Master
Cluster Master Register
Package | Cluster | Contractor | Project Director (PD) | Project Manager (PM) | Construction Manager (CM) | HSE Manager (HSEM) | Section Engineer (SE) | Key
2 | Cluster 7A | TAJV | Hicham Adel Narch | Ghaidh Alfaour | George Deeb | Timur Terakopov | Liqat | 2¦Cluster 7A
2 | Cluster 7B | TAJV | Hicham Adel Narch | Ghaidh Alfaour | George Deeb | Timur Terakopov | Eyad | 2¦Cluster 7B
2 | Cluster 8A | TAJV | Hicham Adel Narch | Ghaidh Alfaour | Mohamed Salama | Timur Terakopov | Ahmad Adel | 2¦Cluster 8A
2 | Cluster 8B | TAJV | Hicham Adel Narch | Ghaidh Alfaour | Mohamed Salama | Timur Terakopov | Ahmad Adel | 2¦Cluster 8B
2 | Cluster 8C | TAJV | Hicham Adel Narch | Ghaidh Alfaour | George Deeb | Timur Terakopov | Ahmad Adel | 2¦Cluster 8C
2 | Cluster 8D | TAJV | Hicham Adel Narch | Ghaidh Alfaour | George Deeb | Timur Terakopov | Ahmad Adel | 2¦Cluster 8D
3 | Cluster 3 | INNOVO | Kahtan Tikriti | Aiman Abdullah | Salama Al Samdy | Mazen Al Atwani | TBD - Update Section Engineer | 3¦Cluster 3
3 | Cluster 4 | INNOVO | Kahtan Tikriti | Aiman Abdullah | Baha Basheer | Mazen Al Atwani | TBD - Update Section Engineer | 3¦Cluster 4
3 | Cluster 5 | INNOVO | Kahtan Tikriti | Michael Ghali | Robair Louies | Mazen Al Atwani | TBD - Update Section Engineer | 3¦Cluster 5
3 | Cluster 6 | INNOVO | Kahtan Tikriti | Michael Ghali | Remon Karas | Mazen Al Atwani | TBD - Update Section Engineer | 3¦Cluster 6
4 | Cluster 1A | TAJV | Hicham Adel Narch | Ghaidh Alfaour | Alaa Hegab | Timur Terakopov | Amr Taha | 4¦Cluster 1A
4 | Cluster 1B | TAJV | Hicham Adel Narch | Ghaidh Alfaour | Hossam Ali Maher | Timur Terakopov | Md Ramadan / Osama Said | 4¦Cluster 1B
4 | Cluster 2A | TAJV | Hicham Adel Narch | Ghaidh Alfaour | Ahmed Salah Hassan Dewidar | Timur Terakopov | Rami Issa | 4¦Cluster 2A
4 | Cluster 2B | TAJV | Hicham Adel Narch | Ghaidh Alfaour | Ahmed Salah Hassan Dewidar | Timur Terakopov | Rami Issa | 4¦Cluster 2B
4 | Cluster 2C | TAJV | Hicham Adel Narch | Ghaidh Alfaour | Ahmed Salah Hassan Dewidar | Timur Terakopov | Salah Nayef | 4¦Cluster 2C

## Lookups
Lookup Lists
Package_List | Cluster_List | Evaluator_Role_List | High_Risk_Activity_List | Yes_No_List | Root_Cause_List | Status_List | KPI_List | Score_List
2 | Cluster 7A | Project Director | Work at Height | YES | Leadership failure | Open | Work at Height Control | 0
3 | Cluster 7B | Project Manager | Edge Protection | NO | Poor supervision | In Progress | Edge Protection | 1
4 | Cluster 8A | Construction Manager | Falling Objects |  | Poor planning | Closed | Falling Object Prevention | 2
| Cluster 8B | HSE Manager | Excavation |  | PTW failure | On Hold | Excavation Safety | 3
| Cluster 8C | Section Engineer | Scaffolding |  | Weak MSRA |  | Scaffolding Compliance | 4
| Cluster 8D | QA/QC | Permit to Work |  | Poor subcontractor control |  | PTW Implementation | 5
| Cluster 3 | KEO | MSRA / Risk Assessment |  | Resource constraint |  | PTW Field Verification
| Cluster 4 | Client | Lifting Operations |  | Inadequate competence |  | MSRA Quality
| Cluster 5 | Other | Traffic Management |  | Poor housekeeping culture |  | Lifting/Precast Installation
| Cluster 6 |  | Housekeeping |  | Interface / simultaneous activity conflict |  | Traffic & Man-Machine Interface
| Cluster 1A |  | Waste Management |  | Other |  | Housekeeping/Waste Management
| Cluster 1B |  | Fire Readiness |  |  |  | Welfare Arrangement
| Cluster 2A |  | Electrical Safety |  |  |  | Fire Readiness
| Cluster 2B |  | Portable Power Tools |  |  |  | Supervision & Subcontractor Control
| Cluster 2C |  | Heat Stress |  |  |  | Temporary Electrical & Tool Safety
Other

## KPI_Weights
KPI Weights and Gate Rules
KPI | Weight | Critical Gate KPI? | Notes
Work at Height Control | 12% | YES | Primary fall prevention and work at height control
Edge Protection | 12% | NO | Continuity and quality of edge protection
Falling Object Prevention | 5% | NO | Exclusion zones, toe boards, debris/tool control
Excavation Safety | 8% | YES | Barricading, access, services, support, spoil setback
Scaffolding Compliance | 10% | YES | Tagging, inspection, full planking, access, stability
PTW Implementation | 8% | YES | Valid PTW, correct scope, signatories, controls
PTW Field Verification | 6% | NO | Physical field verification before permit approval
MSRA Quality | 3% | NO | Task-specific risk assessment and understanding
Lifting/Precast Installation | 10% | YES | Lift plan, appointed person, exclusion, rigging
Traffic & Man-Machine Interface | 6% | NO | Pedestrian segregation, routes, signage, reversing
Housekeeping/Waste Management | 3% | NO | Cleanliness, stacking, access routes, slip/trip control
Welfare Arrangement | 3% | NO | Segregation, storage, transfer/disposal control
Fire Readiness | 5% | NO | Fire points, extinguishers, hot work readiness
Supervision & Subcontractor Control | 3% | NO | Visible supervision and subcontractor control
Temporary Electrical & Tool Safety | 6% | NO | Temporary power, RCD, condition of tools/cables

## Weekly_Inspections
Weekly Inspection Entry Sheet - Full System
Complete only blue-font input cells. Package and Cluster auto-fill leadership, scoring, dashboard, and CAPA logic.
Inspection_ID | Inspection_Date | Week_No | Month | Package | Cluster | Package_Cluster_Check | Contractor | Project Director (PD) | Project Manager (PM) | Construction Manager (CM) | HSE Manager (HSEM) | Section Engineer (SE) | Your_Name | Your_Role | Area_or_Villa | Workers_Observed | Main_High_Risk_Activity | Stop_Work | Work_at_Height | Edge_Protection | Falling_Object_Prevention | Excavation_Safety | Scaffolding_Compliance | PTW_Implementation | PTW_Field_Verification | MSRA_Quality | Lifting/Precast Installation | Traffic_Interface | Housekeeping/Waste Management | Welfare Arrangement | Fire_Readiness | Supervision_Subcontractor | Electrical_Tool_Safety | Total_Score | Raw_Score_% | Weighted_Score_% | Critical_Red_Flag | Award_Eligible | Rating_Band | Repeat_Issue_Seen | Likely_Root_Cause | Top_3_Gaps_Observed | Immediate_Action_Taken | Preventive_Action_Required | Positive_Observations | Action_Owner | Target_Closeout_Date | Evidence_Link_or_Photo | KPI_for_PD_Attention | KPI_for_PM_Attention | KPI_for_CM_Attention | KPI_for_HSEM_Followup | KPI_for_SE_Supervision | Leadership_Visible_Effective | Unsafe_Work_Corrected_Immediately | Best_Improved_Cluster_this_Week | Cluster_Needing_Immediate_Intervention
| 2026-03-26 |  |  | 4 | Cluster 2A | [7 empty] | Godwin | KEO | Villa 8 to 16 |  | Work at Height | YES | 2 | 2 | 3 | 3 | 2 | 3 | 1 | 3 |  | 3 | 1 | 1 | 2 | 1 | 2 | [6 empty] | YES | Leadership failure | 1. Leadership failure 2. Poor supervision 3. Poor sub-contractor control 4. PTW failure | Unsafe work practices were suspended immediately. The CM of the cluster was called but he refused to visit the location. | 1. PTW must be controlled by the main contractor. 2. Close supervision of sub-contractors by main contractor shall be ensured. 3. Non-performing subcontractors shall not be paid and shall be removed from project. 4. Non-performing construction team shall be replaced without delays |  | 1-3rd recommendation by the cluster CM 4th recommendation by the PD. | 2026-04-02
| 2026-03-26 |  |  | 2 | Cluster 8A | [7 empty] | Godwin | KEO | General |  | Scaffolding | NO | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 3 | 4 | 4 | 4 | [6 empty] | NO | Other | No significant gap observed | The team was commended for their visible leadership in driving transformation at Cluster 8A. | The Construction Manager and his team were advised to ensure that sub-contractors do not mess up with their site. 1. No payment for work if site condition is below the acceptable standard. 2. Close supervision of sub-contractors by the construction team of the main contractor. 3. Housekeeping shall be maintained for all shift. 4. Provide a temporary storage area for waste for each villa. 5. PTW shall remain under the control of the main contractor. |  | Construction Manager of Cluster 8A HSE Manager of TAJV | Always
| 2026-03-30 |  |  | 3 | Cluster 4 | [7 empty] | Shinoj | KEO | Villa 8 to 16 | Block work | Edge Protection | NO | 3 | 2 | 3 | 3 | 2 | 4 | 3 | 5 | 1 | 2 | 4 | 2 | 3 | 1 | 3 | [6 empty] | NO | Poor supervision |  | Safety concern identified during site walk. | Improve supervision and close the edge protection gaps before continuation. |  |  | 2026-03-31
Formulas:
Week_No = IF([Inspection_Date]="","",ISOWEEKNUM([Inspection_Date]))

## Weekly_Dashboard
Weekly Dashboard
Selected Week No | 13
Selected Month (yyyy-mm) | 2026-03
Previous Month (yyyy-mm) | 2026-02
Cluster | Package | Contractor | Week Avg Raw % | Week Avg Weighted % | Week Red Flags | Month Avg Raw % | Month Avg Weighted % | Month Red Flags | Month Improvement | Award Eligible | Rank
Cluster 7A
Cluster 7B
Cluster 8A
Cluster 8B
Cluster 8C
Cluster 8D
Cluster 3
Cluster 4
Cluster 5
Cluster 6
Cluster 1A
Cluster 1B
Cluster 2A
Cluster 2B
Cluster 2C
KPI | Selected Week Avg Score | Selected Month Avg Score | Gap to 5 (Week) | Gap to 5 (Month) | Root Cause | Selected Week Count | Selected Month Count
Work at Height Control |  |  |  |  | Leadership failure
Edge Protection |  |  |  |  | Poor supervision
Falling Object Prevention |  |  |  |  | Poor planning
Excavation Safety |  |  |  |  | PTW failure
Scaffolding Compliance |  |  |  |  | Weak MSRA
PTW Implementation |  |  |  |  | Poor subcontractor control
PTW Field Verification |  |  |  |  | Resource constraint
MSRA Quality |  |  |  |  | Inadequate competence
Lifting/Precast Installation |  |  |  |  | Poor housekeeping culture
Traffic & Man-Machine Interface |  |  |  |  | Interface / simultaneous activity conflict
Housekeeping/Waste Management |  |  |  |  | Other
Welfare Arrangement
Fire Readiness
Supervision & Subcontractor Control
Temporary Electrical & Tool Safety

## Monthly_Dashboard
Monthly Dashboard
Selected Month (yyyy-mm) | 2026-03
Previous Month (yyyy-mm) | 2026-02
Cluster | Package | Contractor | Month Avg Raw % | Month Avg Weighted % | Red Flags | Improvement vs Prev Month | Award Eligible | Rank | Open Actions | Overdue Actions
Cluster 7A
Cluster 7B
Cluster 8A
Cluster 8B
Cluster 8C
Cluster 8D
Cluster 3
Cluster 4
Cluster 5
Cluster 6
Cluster 1A
Cluster 1B
Cluster 2A
Cluster 2B
Cluster 2C

## Gap_Analysis
Gap Analysis
Selected Week No | 13
Selected Month (yyyy-mm) | 2026-03
KPI | Week Avg Score | Month Avg Score | Week Gap to 5 | Month Gap to 5 | Week Red Flags | Month Red Flags | Focus
Work at Height Control
Edge Protection
Falling Object Prevention
Excavation Safety
Scaffolding Compliance
PTW Implementation
PTW Field Verification
MSRA Quality
Lifting/Precast Installation
Traffic & Man-Machine Interface
Housekeeping/Waste Management
Welfare Arrangement
Fire Readiness
Supervision & Subcontractor Control
Temporary Electrical & Tool Safety
Root Cause | Week Count | Month Count | Comment
Leadership failure
Poor supervision
Poor planning
PTW failure
Weak MSRA
Poor subcontractor control
Resource constraint
Inadequate competence
Poor housekeeping culture
Interface / simultaneous activity conflict
Other

## CAPA_Tracker
Corrective and Preventive Action (CAPA) Tracker
Automated from Weekly_Inspections. Close Date and Status can be updated manually when an action is fully verified closed.
Action_ID | Date_Raised | Package | Cluster | Contractor | KPI_Area | Finding | Root_Cause | Immediate_Action | Preventive_Action | Action_Owner | Target_Date | Status | Close_Date | Days_Open | Overdue_Flag | Evidence_Link | Helper_Row_Index
Formulas:
Days_Open = IF([Action_ID]="","",IF([Close_Date]<>"",[Close_Date]-[Date_Raised],TODAY()-[Date_Raised]))
Overdue_Flag = IF([Action_ID]="","",IF(AND([Status]<>"Closed",[Target_Date]<TODAY()),"YES","NO"))